## Version 0 Eng
ANNEX III-2 : PO - Kiribati
Term: 2011 ～ 2015 (5years)
| Indicators of Project Purpose | Volume of disposal waste (especially organic waste) is reduced by ●●%
Outputs and Associated Activities |  | Indicators for Outputs | Person in-charge | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC
Steering Committee
Evaluation Studies
OUTPUT 1: | Household waste, especially organic waste is minimized through establishment and promotion of compost | 1-1 # of household exercising home composts | bar: 2011 1
1-1 | Develop a work plan for the baseline survey |  | Kautoa Tonganibeia | bar: 2011 3
1-2 | Conduct baseline survey including study on household waste streams |  | Kautoa Tonganibeia | bar: 2011 5 to 2011 7; 2013 1 to 2013 3; 2015 4 to 2015 6
1-3 | Provide waste storage systems both organic and inorganic wastes for collection by the councils |  | Bweneata Kaoti | bar: 2011 7 to 2011 10
1-4 | Public education and environment awareness program on making compost and home gardens |  | Bweneata Kaoti | bar: 2012 2 to 2013 2
1-5 | Train communities on composting and home gardening |  | Bweneata Kaoti | bar: 2011 8 to 2011 10; 2012 9 to 2012 11
1-6 | Conduct consultation with local communities including farmers on South Tarawa |  | Kautoa Tonganibeia | bar: 2011 8; 2012 10; 2013 10; 2014 10; 2015 10
OUTPUT 2: | Solid Waste Collection of both BTC and TUC is improved. | 2-1 Waste collection is conducted in accordance with the set plan and schedule | bar: 2011 1
2-1 | Develop an effective and separate collection plan for organic and inorganic waste |  | Kautoa Tonganibeia | bar: 2011 6 to 2012 4
2-2 | Train waste collectors with effective ways and means to collect waste, through healthy and safety measures |  | Noketi Karoua | bar: 2012 6; 2014 4
2-3 | Develop the new method and initiatives, such as collecting household waste using honking call, notifying communities to discharge household waste according to the designated collection schedule, etc |  | Kautoa Tonganibeia | bar: 2011 6 to 2012 6
2-4 | Develop a waste collection monitoirng plan |  | Kautoa Tonganibeia | bar: 2012 5 to 2012 6
2-5 | Conduct workshop to improve community awareness on waste collection schedule and new waste collection initiatives |  | Arian Arintetaake | bar: 2011 8; 2012 9; 2013 9; 2014 9; 2015 9
OUTPUT 3: Community awareness on solid waste is improved. |  | 3-1 # of Good practices on 3R identified through the project activities are applied in South Tarawa | bar: 2011 1
3-1 | Prepare educational materials for disseminating experience throughout South Tarawa |  | Ratiata Cati | bar: 2011 10; 2012 11 to 2012 12; 2014 12 to 2015 1
3-2 | Implement the environment communication strategy in terms of solid waste |  | Ratiata Cati
3-3 | Conduct the workshop to disseminate the lessons and experiences learnt |  | Arian Arintetaake | bar: 2013 1; 2015 2

## Version 0 Jap
ANNEX III-2 : PO - キリバス国
実施期間：2011年～2015年（5年間）
| プロジェクト目標の指標： | 最終処分のごみ量（特に有機性ごみ）が●●%減少する
アウトプットと関連の活動項目 |  | アウトプットの指標 | キリバス側担当者 | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
定期会議 調査等 | 合同調整委員会 (JCC)
ステアリング・コミッティ（SPREP 総会）
評価調査
アウトプット1:家庭ごみ、特に有機性ゴミがコンポスト化の確立と普及促進によって減量化される。 |  | 1-1 家庭でコンポストづくりを実践している世帯数 | bar: 2011 1
1-1 | ベースライン調査の実施に向けた調査計画を作成する。 |  | Kautoa Tonganibeia | bar: 2011 3
1-2 | 家庭から排出されるごみ質の調査を含むベースライン調査を実施する。 |  | Kautoa Tonganibeia | bar: 2011 5 to 2011 7; 2013 1 to 2013 3; 2015 4 to 2015 6
1-3 | BTC（ベシオ町役場）とTUC（テイナイナイ自治体）によって収集される有機質ごみ及び無機性廃棄物の、保管システムを用意する。 |  | Bweneata Kaoti | bar: 2011 7 to 2011 10
1-4 | コンポスト及び家庭菜園づくりに関する住民向けの教育や環境啓発を行う。 |  | Bweneata Kaoti | bar: 2012 2 to 2013 2
1-5 | コンポスト及び家庭菜園づくりに関するコミュニティ向けの研修を行う。 |  | Bweneata Kaoti | bar: 2011 8 to 2011 10; 2012 9 to 2012 11
1-6 | 南タラワの農民を含め地元コミュニティとのコンサルテーションを開催する。 |  | Kautoa Tonganibeia | bar: 2011 8; 2012 10; 2013 10; 2014 10; 2015 10
アウトプット2: BTCとTUCにおいてごみの収集状況が改善される。 |  | 2-1 ごみ収集が決められた計画と収集スケジュールに基づいて行われる | bar: 2011 1
2-1 | 有機質ごみ及び無機性廃棄物について、効果的で収集日を分けた収集計画（例えばごみ収集カレンダー）を作成する。 |  | Kautoa Tonganibeia | bar: 2011 6 to 2012 4
2-2 | ごみ収集作業員対して、衛生及び安全対策を含めた効果的な方法及びごみ収集手段に関する研修を行う。 |  | Noketi Karoua | bar: 2012 6; 2014 4
2-3 | ごみ収集車両からの音声案内やコミュニティ毎にごみ収集日を設定することの周知等、新たなごみ収集方法や取組み方針を策定する。 |  | Kautoa Tonganibeia | bar: 2011 6 to 2012 6
2-4 | ごみ収集状況に関するモニタリング計画を作成する。 |  | Kautoa Tonganibeia | bar: 2012 5 to 2012 6
2-5 | ごみ収集スケジュールや新たなごみ収集の取り組み方針について、住民に周知徹底させるためのワークショップを開催する。 |  | Arian Arintetaake | bar: 2011 8; 2012 9; 2013 9; 2014 9; 2015 9
アウトプット３: ごみに関して、コミュニティにおける啓発状況が改善される。 |  | 3-1 プロジェクト活動を通して見いだされた３Ｒに関する好事例が南タラワにおいて用いられた数 | bar: 2011 1
3-1 | 南タラワ全域においてグッドプラクティス（好事例）普及を目的とした教材を作成する。 |  | Ratiata Cati | bar: 2011 10; 2012 11 to 2012 12; 2014 12 to 2015 1
3-2 | ごみ問題解決に資する環境コニュニケーション戦略を実施に移す。 |  | Ratiata Cati
3-3 | これまでの実践を通じて得られた学びや経験を普及するためのワークショップを開催する。 |  | Arian Arintetaake | bar: 2013 1; 2015 2

## Version 2 (130130) Eng
PO - Kiribati
Term: 2011 ～ 2015 (5years)
| Indicators of Project Purpose | Volume of disposal waste (especially organic waste) is reduced by 5% | [61 empty] | Version 4
Date issued: 10th of February, 2015
Outputs and Associated Activities |  | Indicators for Outputs | Organization in-charge |  | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC
Steering Committee
Evaluation Studies
OUTPUT 1: | Household waste, especially green waste is recycled through waste separation and chipping (recycling of organic waste) | 1-1 5% of households (of South Tarawa) using compost 1-2 The amount of green waste for recycling (compost, firewood, etc.) is increased at Betio landfill site. (5% of recycling rate) | bar: 2011 1
1-1 | Development of a work plan for the baseline survey |  | ECD | Plan | bar: 2011 8 to 2011 11
Actual | bar: 2011 8 to 2011 11
1-2 | Conducting of baseline surveys |  | ECD | Plan | bar: 2011 10 to 2012 2; 2013 11 to 2014 1; 2015 9 to 2015 11
Actual | bar: 2011 10 to 2012 2; 2013 10 to 2013 11
1-3 | Conducting trial of home composting using compost bins |  | BTC | Plan | bar: 2011 11 to 2012 4
Actual | bar: 2011 11 to 2012 12
1-4 | Making compost at BTC from green waste |  | BTC | Plan | bar: 2012 7 to 2015 12
Actual | bar: 2012 4 to 2014 11
1-5 | Conduction public education and environment awareness program on the importance of waste minimization and waste separation |  | BTC, TUC, ECD (MPA), ALD | Plan | bar: 2012 5 to 2015 10
Actual | bar: 2013 2; 2014 9 to 2014 12
1-6 | Promoting the use of wood chips and fire woods |  | BTC, TUC, ALD | Plan | bar: 2012 9 to 2015 10
Actual | bar: 2013 10 to 2015 2
1-7 | Establishing financial system for shredder operation at BTC |  | BTC | Plan | bar: 2014 1 to 2015 12
Actual | bar: 2014 1 to 2015 2
OUTPUT2: | Community awareness on solid waste is improved through Clean School Program. | 2-1 seven schools of South Tarawa is implementing the Clean School Program. | bar: 2011 1
2-1 | promoting 3R related activities at schools through Clean School Program |  | ECD (MPA), TUC, BTC | Plan | bar: 2012 5 to 2015 12
Actual | bar: 2012 5 to 2013 2; 2013 6 to 2013 7; 2013 11 to 2014 3; 2014 8; 2014 12; 2015 2
2-2 | Conducting of workshop to disseminate the lessons and experiences learnt |  | ECD (MPA) | Plan | bar: 2013 1; 2015 10
Actual | bar: 2013 2
|  | * | ECD: Environment and Conservation Division, MELAD
BTC: Betio Town Council
TUC: Teinainao Urban Council