## PDM Mar2015
Attachment 1: Project Design Matrix (PDM) - PNG |  |  |  |  | PDM: Version 2 (3/2015)
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of DEC and NCDC |  |  | Final Beneficiaries: Citizens of Papua New Guinea |  | Project period: Feb, 2011 - Feb, 2015 (5 years)
Implementing Agency: NCDC |  |  | Target Area: National Capital District |  | Date issued (revised): March 2015
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced |  |  | 1. The importance of waste minimization is understood and more than one waste minimization scheme is practiced in NCDC. | Implementation report on waste minimization schemes
Project Purpose |  |  |  |  | 1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 1. Four (4) Experts (Trainers) are listed in the SPREP inventory | SPREP (Regional inventory of skilled people)
|  |  | 2. Landfill management/ collection services are implemented according to the SWM plan. | SWM Plan implementation
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing
2-1 | 3Rs/4Rs
2-2 | Waste Disposal | Output 1:Solid waste disposal facility and operation is improved. | 1-1 Baruni upgrading plan is prepared and implemented 1-2 Operation and maintenance manual is prepared and implemented | 1-1 Implementation Report 1-2 Monitoring Report
2-3 | Waste Collection | Output 2: Waste collection in Port Moresby is improved | 2-1 Collection coverage is increased to 70% 2-2. Number of complaints are reduced by 30% 2-3 One time-and -motion study conducted by NCDC itself annually | 2-1 Operation report (Amount of waste collected, average # of trips per day) 2-2 Complaints Register 2-3 Study Report
3 | Legislation
4 | Awareness/Communication/Education
5 | Capacity Building
6 | Environmental Monitoring
7 | Policy,Planning, Performance | Output 3: Capacity of planning and monitoring of Solid Waste Management in Port Moresby (National Capital District: NCDC) is increased | 3-1. SWM plan is adopted 3-2. Solid waste management budget is preparaed and SWM expendututre is analysed for FY 2015 | 3-1 Publication of the Plan 3-2 Budget analysis report
8 | Solid Waste Industry
* | Monitoring system of RS2010
Activities |  |  | Inputs
|  | Please see PO for details. | Japanese Side | PNG side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated from the government.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space Funds for EIA (NCDC) Cost sharing for rehabilitation of Baruni landfill
|  |  | Local cost support |  | Pre-condition