## PO Mar-2015
ANNEX IV : PO - Papua New Guinea
Term: 2011 - 2015 (5years) | [58 empty] | March 2015
| Indicators of Project Purpose | 1. Four (4) Experts (Trainers) are listed in the SPREP inventory 2. Landfill management/ collection services are implemented according to the SWM plan
Outputs and Associated Activities |  | Indicators for Outputs | Person in-charge | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC |  | Joshua Sam/ Janet Haua/ Dianna Wapyer
Steering Committee
Evaluation Studies
OUTPUT 1: | Solid waste disposal facility and operation is improved | 1-1 Baruni upgrading plan is prepared and implemented 1-2 Operation and maintenance manual is prepared and implemented | Simeon Terina
1-1 | Conduct site investigation into Baruni dumpsite |  | Completed
1-2 | Develop a work plan for the rehabilitation of the Baruni dump |  | James
1-3 | Undertake Environment Permit application process in order to obtain and Environment Permit |  | Completed
1-4 | Undertake upgrading work on the rehabilitation of the Baruni dump |  | James/ Simeon/ Walter/ Kaupa
1-5 | Develop an operation & maintenance manual for Baruni dump |  | Simeon/ Walter
1-6 | Establish water monitoring system and implementation |  | Walter/ Simeon
1-7 | Conduct training for both for landfill management staff and operators |  | Simeon/ James/ Walter
1-8 | Monitor operations of the upgraded landfill and evaluate its efficiency |  | James/Simeon and Senior Officers
OUTPUT 2: | Waste collection in Port Moresby is improved | 2-1 Collection coverage is increased to 70% 2-2 Number of complaints are reduced by 30% 2-3 One time-and -motion study conducted by NCDC itself annually | John Navara (left WMD 1/2015)/ Vivianne Morofa
2-1 | Develop work plan to carry out time-and-motion study |  | Completed | bar: 2011 12; 2012 12; 2013 12; 2014 12; 2015 12
2-2 | Undertake time-and-motion study |  | Paul/ Vivianne/ Kupil (on study leave)
2-3 | Analyse results and generate study report |  | Paul/ Vivianne
2-4 | Make amendments to the contracts for the waste collection contractors |  | John (left WMD)/ Vivianne/ Joshua
2-5 | Conduct training for all contractors |  | John (left WMD)/ Vivianne/ Paul/ Janet/ Racheal
2-6 | Monitor and evaluate at scheduled intervals |  | John (left WMD)/ Vivianne/ Paul and the supervisors for solid waste
OUTPUT 3: | Capacity of planning and monitoring of Solid Waste Management in Port Moresby (National Capital District: NCDC) is increased | 3-1 SWM Plan is developed and adopted 3-2 Solid Waste Management budget is prepared and SWM expenditure is analyzed for FY2015 | Ronnie Ranu (supported by Joshua/ Janet)
3-1 | Promotion of 3Rs for inclusion in plan (3R HEART Program and study for Gereh Market Green Waste Compost) |  | John (left WMD)/ Nanai/ Paul/ Racheal
3-2 | Develop work plan for the waste characterization exercise |  | Ronnie (supported by Joshua/ Janet) | bar: 2014 12; 2015 12
3-3 | Undertake waste characterization exercise |  | Ronnie/ Vivianne/ Kupil (on study leave)/ Nanai | bar: 2014 12
M
3-4 | Analyze results and generate report |  | Ronnie/ Vivianne/ Kupil (on study leave)/ Nanai
M
3-5 | Develop Solid Waste Management Plan for Port Moresby |  | Joshua/ Ronnie/ Vivianne
3-6 | Adoption of Waste Plan by DEC and NCDC managements |  | Janet and Joshua
3-7 | Implement and monitor the Waste Management Plan |  | Joshua and Senior waste management officers
| Original schedule | Actual schedule |  | 2011 1: Revised schedule (as of March, 2015)
Note on BA46: G70713: Industrial waste audit
Note on BC46: G70713: Gerehu Market Waste Survey