## Annex III (PO 2014)
Annex III: Modified PO in Marshall Islands Ver.3 (30-Jan, 2015) | [7 empty] | :Done | [11 empty] | :Scheduled or not yet | [13 empty] | :Scheduled
30/1/2015
Outputs and Associated Activities <Modification> |  | Indicators for Outputs | Dept. & Agencies in Charge (Role-sharing is detailed in Annex IV) | Technical Assistance | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Output 1: NSWMS is implemented. |  | 1-1 NSWMS and Action plan of Majuro is finalized. 1-2 Implementation of Action plan is monitored and reviewed by the Monitoring Committee 3 times a year. 1.3. Progress report is issued annualy.
1-1 | Develop the action plan of NSWMS. |  | OEPPC | JICA/SPREP | bar: 2014 9
1-2 | Conduct the dissemination workshop on NSWMS/Action plan for key stakeholders. |  | OEPPC | JICA | bar: 2012 6
1-4 | Monitoring, Check and Review on NSWMS/Action plan |  | OEPPC | JICA | bar: 2013 10 to 2013 11; 2014 7; 2014 10; 2015 1; 2015 6; 2015 10
1-4-1 | Rising capability on waste collection system. |  | MAWC | bar: 2012 10; 2013 9
1-5 | Modify the NSWMS based on the result of activities. > Detail is shown as follow. |  | OEPPC
1-5-1 | Review and monitor progress of NSWMS/AP by the Monitoring Committee* *Monitoring Committee: OEPPC(Chair), MPW, MAWC,EPA,MOE |  | OEPPC | bar: 2013 10 to 2013 11; 2014 10; 2015 1; 2015 6; 2015 10
1-5-2 | Review and Modify the NSWMS in accordance with activities of the Monitoring Committee |  | OEPPC | JICA | bar: 2013 10 to 2013 11; 2014 10; 2015 1; 2015 6; 2015 10
1-6 | Draft the next NSWMS for the year 2016-2020.(This activity should be erase in case cuttent NSWMS covers year of 2015) |  | OEPPC | (SPREP)
1-7 | PROGRESS REPORT |  | OEPPC | JICA | bar: 2015 12
Output 2 : Recycling system is improved in Majuro. |  | 2-1 Recycle products is increased year by year. 2-2 # of collected and exported materials are increasing year by year.
2-1 | Review the existing survey for waste volume, waste composition. |  | MAWC | JICA | bar: 2011 7
2-2 | Identify the marketable recyclables |  | MAWC/EPA | bar: 2011 8 to 2011 9
2-3 | Develop the conceptual plan of recycling system |  | OEPPC、(MAWC) | JICA | bar: 2014 9
2-5 | Conduct the awareness raising activities for Majuro. |  | EPA (MAWC, MICS) | bar: 2012 3 to 2013 1
2-8 | Review and monitor progress on output2 by the monitoring committee |  | OEPPC、(MAWC) | JICA | bar: 2013 10 to 2013 11; 2014 7; 2014 10; 2015 1; 2015 6; 2015 10
OUTPUT 3 : Composting system is improved in Majuro. |  | 3-1 Volume of compost production are increased in Majuro
3-1 | Conduct the survey for quality improvement of compost from green waste. |  | MAWC | JICA | bar: 2012 4 to 2012 5
3-5 | Review and monitor progress on output3 by the monitoring committee |  | OEPPC | JICA | bar: 2013 10 to 2013 11; 2014 7; 2014 10; 2015 1; 2015 6; 2015 10
OUTPUT 4 : School-based recycle system is introduced in Majuro. |  | 4-1 Manual/material of awareness raising is developed. 4-2 Campaign activities are conducted on regular schedule. 4-3 I-Recycle programs are implemented in over 80% of elementary schools in Majuro.
4-1 | Develop the implementation plan for awareness raising and environmental education |  | MOE,(EPA, MAWC, OEPPC) | bar: 2011 7 to 2011 9; 2012 3 to 2012 5
4-2 | Conduct training of school-based recycle system including awareness/ environmental education to the organizations concerned. |  | MOE,(EPA, MAWC, OEPPC) | bar: 2013 1
4-3 | Select the target schools (public elementary schools). |  | MOE,(EPA, MAWC, OEPPC) | bar: 2011 12
4-4 | Conduct training on awareness and environmental education for school teachers. |  | MOE,(EPA, MAWC, OEPPC) | JICA | bar: 2013 1
4-5 | Implement the school-based recycle system |  | MOE,(EPA, MAWC, OEPPC) | bar: 2012 4 to 2013 2
4-6 | Conduct thecampaign activities. |  | MOE,(EPA, MAWC, OEPPC) | bar: 2013 9
4-13 | Review and monitor progress on output4 by the monitoring committee |  | OEPPC | JICA | bar: 2013 10 to 2013 11; 2014 10; 2015 1; 2015 6; 2015 10
Output 5 : Solid waste management system is improved in Ebeye. |  | 5-1 Plan for improvement of waste collection is drafted. 5-2 The burning in the open dumping decreased to 0 in Ebye. 5-3 The waste is located separately and adequately in dump site. 5-4 Bulky waste collection is separated from the common household waste. 5-5 Education on 4R promotion is conducted for all school classroom. 5-6 teacher training on 4R promotion is conducted for all teachers in Ebeye. 5-7 Plan for paper fuel is drafted | Chief person: KAL Gov.(Aeto)
5-1 | Conduct the survey for waste volume and waste composition. |  | KALGov | JICA | bar: 2013 5; 2015 1
5-2 | Develop the action plan of SWMS/Action Plan for Ebeye. |  | KALGov | bar: 2014 10
5-3 | Select the priority activities. |  | KALGov | JICA | bar: 2012 11
5-3-1 | Develop teaching materials such as booklet, powerpoint and other materials |  | KALGov | JICA | bar: 2013 11
5-3-2 | Develop plan and implementation on school education and teacher training for 4R promotion |  | KALGov/EPA/MOE | JICA | bar: 2013 11; 2014 7; 2015 1
5-3-3 | Implementation of Waste composition survey |  | KALGov | JICA | bar: 2013 5; 2015 1
5-3-4 | Draft improvement plan on collection-fee system and other waste collection program |  | KALGov | JICA | bar: 2014 10; 2015 3
5-3-5 | Improvement of dump site. |  | KALGov | JICA | bar: 2013 3; 2013 5 to 2013 6; 2014 10 to 2015 1; 2015 5 to 2015 6
5-3-6 | Launching producing "Paper Fuel" |  | KALGov | bar: 2015 5 to 2015 9
4R: Refuse, Reduce, Reuse, Recycle
W/S
Time and Motion Study
We are here now
Majuro
Training
Pohnpei
Training
Training
Training
Starting
the New Waste Collection
System
Postponed

## Annex II Result in 2014
Annex II: The Result of the PO Activities in 2014 | [8 empty] | :Done | [11 empty] | :Scheduled or not yet | [13 empty] | :Scheduled
30/1/2015
Outputs and Associated Activities |  | Indicators for Outputs | RESULT in 2014 | Dept. & Agencies in Charge | Technical Assistance | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Output 1: NSWMS is implemented. |  | 1-1 NSWMS and Action plan of Majuro is finalized. 1-2 Implementation of Action plan is monitored and reviewed by the Monitoring Committee 3 times a year. 1.3. Progress report is issued annualy.
1-1 | Develop the action plan of NSWMS. |  | The draft strategy was finalized and formally submitted to the Cabinet for endorsement. A special briefing meeting was held with Minister in Assistance to the President to review the strategy and action plan. | OEPPC | JICA/SPREP | bar: 2014 9
1-2 | Conduct the dissemination workshop on NSWMS/Action plan for key stakeholders. |  |  | OEPPC | JICA | bar: 2012 6
1-4 | Monitoring, Check and Review on NSWMS/Action plan |  | Several meetings were conducted in November to review and revise the draft monitoring sheet | OEPPC | JICA | bar: 2013 10 to 2013 11; 2014 10; 2015 1; 2015 6; 2015 10
1-4-1 | Rising capability on waste collection system. |  |  | MAWC | bar: 2012 10; 2013 9
1-5 | Modify the NSWMS based on the result of activities. > Detail is shown as follow. |  | Plan to hold meeting at end of 2015 | OEPPC
1-5-1 | Review and monitor progress of NSWMS/AP by the Monitoring Committee* *Monitoring Committee: OEPPC(Chair), MPW, MAWC,EPA,MOE |  |  | OEPPC | bar: 2013 10 to 2013 11; 2014 10; 2015 1; 2015 6; 2015 10
1-5-2 | Review and Modify the NSWMS in accordance with activities of the Monitoring Committee |  |  | OEPPC | JICA | bar: 2013 10 to 2013 11; 2015 6; 2015 10
1-6 | Draft the next NSWMS for the year 2016-2020.(This activity should be erase in case cuttent NSWMS covers year of 2015) |  | This activity should be erase in case cuttent NSWMS covers year of 2015) | OEPPC | (SPREP) | bar: 2015 2 to 2015 8
1-7 | PROGRESS REPORT |  | Meetings held with stakeholders to discuss way forward and templates to be drafted in 2015 | OEPPC | JICA | bar: 2015 12
Output 2 : Recycling system is improved in Majuro. |  | 2-1 Recycle products is increased year by year. 2-2 # of collected and exported materials are increasing year by year.
2-1 | Review the existing survey for waste volume, waste composition. |  |  | MAWC | JICA | bar: 2011 7
2-2 | Identify the marketable recyclables |  |  | MAWC/EPA | bar: 2011 8 to 2011 9
2-3 | Develop the conceptual plan of recycling system |  | Concept of recycle is included in the NSWMS | OEPPC、(MAWC) | JICA | bar: 2014 9
2-5 | Conduct the awareness raising activities for Majuro. |  |  | EPA (MAWC, MICS) | bar: 2012 3 to 2013 1
2-8 | Review and monitor progress on output2 by the monitoring committee |  | Same as the result of Output1-4 | OEPPC、(MAWC) | JICA | bar: 2013 10 to 2013 11; 2014 7; 2014 10; 2015 1; 2015 6; 2015 10
OUTPUT 3 : Composting system is improved in Majuro. |  | 3-1 Volume of compost sales production are increased in Majuro
3-1 | Conduct the survey for quality improvement of compost from green waste. |  |  | MAWC | JICA | bar: 2012 4 to 2012 5
3-5 | Review and monitor progress on output3 by the monitoring committee |  | Same as the result of Output1-4 | OEPPC | JICA | bar: 2013 10 to 2013 11; 2014 7; 2014 10; 2015 1; 2015 6; 2015 10
OUTPUT 4 : School-based recycle system is introduced in Majuro. |  | 4-1 Manual/material of awareness raising is developed. 4-2 Campaign activities are conducted on regular schedule. 4-3 I-Recycle programs are implemented in over 80% of elementary schools in Majuro.
4-1 | Develop the implementation plan for awareness raising and environmental education |  |  | MOE,(EPA, MAWC, OEPPC) | bar: 2011 7 to 2011 9; 2012 3 to 2012 5
4-2 | Conduct training of school-based recycle system including awareness/ environmental education to the organizations concerned. |  |  | MOE,(EPA, MAWC, OEPPC) | bar: 2013 1
4-3 | Select the target schools (public elementary schools). |  |  | MOE,(EPA, MAWC, OEPPC) | bar: 2011 12
4-4 | Conduct training on awareness and environmental education for school teachers. |  |  | MOE,(EPA, MAWC, OEPPC) | JICA | bar: 2013 1
4-5 | Implement the school-based recycle system |  |  | MOE,(EPA, MAWC, OEPPC) | bar: 2012 4 to 2013 2
4-6 | Conduct thecampaign activities. |  |  | MOE,(EPA, MAWC, OEPPC) | bar: 2013 9
4-13 | Review and monitor progress on output4 by the monitoring committee |  | Same as the result of Output1-4 | OEPPC | JICA | bar: 2013 10 to 2013 11; 2014 7; 2014 10; 2015 1; 2015 6; 2015 10
Output 5 : Solid waste management system is improved in Ebeye. |  | 5-1 Plan for improvement of waste collection is drafted. 5-2 The burning in the open dumping decreased to 0 in Ebye. 5-3 The waste is located separately and adequately in dump site. 5-4 Bulky waste collection is separated from the common household waste. 5-5 Education on 4R promotion is conducted for all school classroom. 5-6 teacher training on 4R promotion is conducted for all teachers in Ebeye. 5-7 Plan for paper fuel is drafted |  | Chief person: KAL Gov.(Aeto)
5-1 | Conduct the survey for waste volume and waste composition. |  | A training on waste survey was conducted in January, 2015. The Survey is acheduled in January, 2015. | KALGov | JICA | bar: 2013 5; 2015 1
5-2 | Develop the action plan of NSWMS/Action Plan for Ebeye. |  | The Action Plan was developed in November, 2014. | KALGov | bar: 2014 10
5-3 | Select the priority activities. |  | Selected in 2013 as bellow. | KALGov | JICA | bar: 2012 11
5-3-1 | Develop teaching materials such as booklet, powerpoint and other materials |  | EPA & KALG developed presentation materials and the materials were used at the awareness and education activities. | KALGov | JICA | bar: 2013 11
5-3-2 | Develop plan and implementation on school education and teacher training for 4R promotion |  | The schoo leducation was conducted by EPA,Teacher training was not conducted after November,2013. | KALGov/EPA/MOE | JICA | bar: 2013 11; 2014 7; 2015 1
5-3-3 | Implementation of Waste composition survey |  | The waste composition survey (training) was conducted in January, 2015. | KALGov | JICA | bar: 2013 5; 2015 1
5-3-4 | Draft improvement plan on collection-fee system and other waste collection program |  | The improvement plan on waste collection was developed in November, 2014. | KALGov | JICA | bar: 2014 10
5-3-5 | Improvement of dump site. |  | The field work on improvement of the dumpsite was conducted in November, 2014. The improvement work has been conducted continuously. | KALGov | JICA | bar: 2013 3; 2013 5 to 2013 6; 2014 10 to 2015 1
5-3-6 | Launching producing "Paper Fuel" |  | >>Postpone to 2015 | KALGov
4R: Refuse, Reduce, Reuse, Recycle
W/S
Time and Motion Study
We are here now
Majuro
Training
Pohnpei
Training
Training
Training
Submitted and
Briefed