## Annex I PDM
ANNEX I: Project Design Matrix (PDM) - Marshall Islands |  |  |  | PDM: Version 1 (7-Feb,2014)
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of OEPPC, MPW, EPA, MAWC, MLG, KALGov. MOE |  | Final Beneficiaries: Citizens of Marshall Islands |  | Project period: 5 years
Implementing Agency: OEPPC, MPW, EPA, MAWC, MLG, KALGov., MOE |  | Target Area: Marshall Island (Majuro and Ebeye)
Narrative Summary |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced |  | 1.Good practices developed in Marshall Islands is implemented in other island countries tackling with common issues 2.At least one training/workshop in the region which is conducted by facilitators/trainers from Marshall Islands | 1．Report of activities on experience sharing 2．Records of training/workshop organized by counterparts in Marshall Islands
Project Purpose |  |  |  | 1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  | 1. 6 experts (Trainers) listed in the SPREP inventory | 1.SPREP (Regional inventory of skilled people)
|  | 2. Good practices and experience are shared among Majuro and other Atoll Local Governments. | 2.Records on cooperation activities/actions.
# | Outputs
1 | NSWMS is implemented. | 1-1 NSWMS and Action plan of Majuro is finalized. 1-2 Implementation of Action plan is monitored and reviewed by the Monitoring Committee 3 times a year. 1-3 Progress report is issued annualy. | 1-1 Finalized NSWMS and Action plan 1-2 Reports/check results of Monitoring presented for the Monitoring committee**. **Monitoring Committee: OEPPC(Chair), MPW, MAWC, EPA, MOE 1-3 Annual progress report
2 | Recycling system is improved in Majuro. | 2-1 Recycle products is increased year by year. 2-2 # of collected and exported materials are increasing year by year. | 2-1& 2-2 Reports/check results of Monitoring presented for the Monitoring committee.
3 | Composting system is improved in Majuro. | 3-1 Volume of compost production are increased in Majuro | 3-1 Reports/check results of Monitoring presented for the Monitoring committee.
4 | School-based recycle system is introduced in Majuro. | 4-1 Manual/material of awareness raising is developed. 4-2 Campaign activities are conducted on a regular schedule. 4-3 I-Recycle programs are implemented in over 80% of elementary schools in Majuro. | 4-1Manual and Materials 4-2 &4-3 Reports/ check results of Monitoring presented for the Monitoring Committee.
5 | Solid waste management system is improved in Ebyeye. | 5-１ Plan for improvement of waste collection is drafted. | 5-1Plan for improvement of waste collection
|  | 5-2 The burning in the open dumping decreased to 0 in Ebye. 5-3 The waste is located separately and adequately in dump site. 5-4 Bulky waste collection is separated from the common household waste. | 5-2,5-3&5-4 Evaluation results of Management level on dump site
|  | 5-5 Education on 4R promotion is conducted for all school classroom. 5-6 Teacher training on 4R promotion is conducted for all teachers in Ebeye. *4R: Refuse, Reduce, Reuse, Recycle | 5-5&5-6Records on education activities/actions on 4R promotion.
|  | 5-7 Plan for paper fuel is drafted | 5-7 Drafted plan for paper fuel.
Activities |  | Inputs
| Please see PO for details. | Japanese Side | Marshall Islands side | 1.Counterpart personnel keep working in the field of SWM. 2. Necessary budget to carry out activities is allocated from the government.
|  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  | Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  | Loca cost support |  | Pre-condition
Cooperation of community people of the target area is obtained.
* | OEPPC= Office of Environmental Planning and Policy Coordination, MPW=Ministry of Public Works, EPA=Environmental Protection Authority, MAWC=Marshall Atoll Waste Company, MLG=Majuro Atoll Local Government, KALGov.=Kwajalein Atoll Local Government, MICS=Marshall Islands Conservation Society, NSWMS=National Solid Waste Management Strategy