## PO Apr2015
Plan of Operation (PO) - Samoa
Project Term: 2011 ～ 2015 (5years) |  | 1. Two (2) Experts (Trainers) are listed in the SPREP inventory
| Indicators for Project Purpose: | 2. Amount of waste disposal is decreased by at least 5%
Version 4 as of 29th April 2015
Outputs and Associated Activities |  | Indicators for Outputs | Person in-charge | Progress | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC
Steering Committee
Evaluation Studies
OUTPUT 1: | WASTE MINIMIZATION MEASURES AND PRACTICES ARE INTRODUCED AND IMPLEMENTED AT THE URBAN AREAS | 1-1 Four (4) waste survey reports are produced. 1-2 Four (4) communities and nine (9) businesses participated in waste segregation/ minimization 1-3 Amounts of recyclable wastes collected increase 10%. 1-4 Four (4) public consultation/ hearing meeting/ workshops for waste minimization regulations/ strategy
1-1 | Conduct Solid Waste Characterization Study |  | Ms Faatamalii Meredith / Ms Pesio Tutagalevao | Planned
Actual
1-2 | Conduct Time and Motion Study |  | Ms Faatamalii Meredith / Ms Pesio Tutagalevao | Planned
Actual
1-3 | Prepare and finalize project plan for waste minimization |  | Ms Faatamalii Meredith | Planned
Actual
1-4 | Develop and setup Public-Private Partnership with Pacific Recycler Company - collection and return of certain waste |  | Mr Setoa Apa / Mr Seumanu Mikaele | Planned
Actual
1-5 | Conduct consultation and public awareness to promote segregation at source and collection of approved waste under PPP |  | Mr Setoa Apo | Planned
Actual
1-6 | Implement Pilot Project - segregation and collection of recyclable waste items under PPP |  | Mr Seumanu Mikaele / Ms Faatamalii Meredith | Planned
Actual
1-7 | Review the Pilot Project |  | Ms Faatamalii Meredith / Ms Pesio Tutagalevao | Planned
Actual
1-8 | Develop a Waste Minimization Strategy |  | Mr Setoa Apo | Planned
Actual
1-9 | Develop Draft Framework of Regulation for Container Deposit Levies to support the recover and return of identified waste under the Pilot project |  | Mr Setoa Apo / Ms Faatamalii Meredith | Planned
Actual
1-10 | Review Regulation on Biodegradable shopping bags |  | Mr Setoa Apo | Planned
Actual
OUTPUT 2: | TAFAIGATA IS OPERATED AS A REGIONAL WASTE DISPOSAL FACILITY WITH IMPROVEMENTS AT VAIAATA IN PLACE | 2-1 Tafaigata land use and development plan produced 2-2 Incoming waste data are recorded and periodically reported (monthly) using the weighbridge system at Tafaigata 2-3 Improved quality of leachate at Vaiaata landfill 2-4 Management and control of waste pickers are checked daily.
2-1 | Produce a Tafaigata Draft Master Landuse and Development Plan |  | Mr Seumanu Mikaele | Planned
Actual
2-2 | Introduce measures to control waste picking |  | Mr Seumanu Mikaele | Planned
Actual
2-3 | Enforce waste segreation for the incoming commercial waste |  | Mr Seumanu Mikaele | Planned
Actual
2-4 | Install signs at different zones and waste disposal facilities at Tafaigata |  | Mr Falaniko Tino | Planned
Actual
2-5 | Install an electronic waste recording system at Tafaigata and provide training for staff on maintenance and operation. |  | Mr Seumanu Mikaele | Planned
Actual
2-6 | Plan and make improvements to the leachate quality and treatment facilities at Vaiaata landfill |  | Mr Seumanu Mikaele/Mr.Lucie Isaia | Planned
Actual
2-7 | Monitor and enforce conditions for existing waste facilities at Tafaigata |  | Mr Lameko Tasimale / Mr Seumanu Mikaele/Technical Committee | Planned
Actual
2-8 | Conduct Leachate Monitoring at Tafaigata and Vaiaata |  | Senior Chemical OfficerMr. Lucie Isaia/ Ms Faatamalii Meredith/ Ms Pesio Tutagalevao | Planned
Actual
OUTPUT 3: | Output 3: Experiences and lessons learnt are shared in both national and international levels | 3-1 Newsletters are produced twice a year and at least one relevant document is produced. 3-2 Four (4) overseas missions of PIC counterparts and national stakeholders are hosted. 3-3 At least five (5) regional and international workshops participated to present Samoa's experiences
3-1 | Produce Newsletters twice a year to share collected results and achievements |  | Ms Faatamalii Meredith / Ms Pesio Tutagalevao | Planned
Actual
3-2. | Accept overseas missions and attachments of PIC counterparts |  | Mr Setoa Apo /Mr Seumanu Mikaele / Ms Faatamalii Meredith / Ms Pesio Tutagalevao | Planned
Actual
3-3 | Participate and share project progresses and lessons learnt at regional and international workshops |  | Mr Setoa Apo/Mr Seumanu Mikaele / Ms Faatamalii Meredith / Ms Pesio Tutagalevao | Planned
Actual
| Activity planned before Feb. 2014 | Activity rescheduled after Feb. 2014 | Actual implementation | Activities planned in 2015
Savaii
B1,B2
Rural