## Vol.0
Project Design Matrix (PDM) - Solomon Islands |  |  |  |  | PDM: Version 0
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of MECM, HCC and Gizo Town |  |  | Final Beneficiaries: Citizens of Solomon Islands |  | Project period: ●●, 2011 - ●●, 2015 (5 years)
Implementing Agency: MECM, HCC and Gizo Town |  |  | Target Area: Solomon Islands |  | Date issued: Month / Date, 2010
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced. |  |  | 1.To be discussed | To be advised
1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Project Purpose |  |  | 1. # of experts (Trainers) in the field of ●● listed in the SPREP inventory | SPREP (Regional inventory of skilled people)
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 2-1 #of initiatives on waste minimization introduced 2-2 Proportion of recyclables and green waste disposed of at the landfill is decreased by XX % | 2-1 Workshop presentation 2-2 Waste characterization reports
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing
2-1 | 3Rs/4Rs | Output 1: 3R activities are practiced in Honiara and Gizo | 1-1 3R strategy is developed. | 1-1 Strategy paper for 3R
2-2 | Waste Disposal | Output 2: Waste disposal system is improved in Honiara and Gizo. | 2-1 Landfills are operated by the trained staff according to the operation manuals developed by the project | 2-1 Operation manuals 2-2 Operation reports
2-3 | Waste Collection
3 | Legislation
4 | Awareness/Communication/Education | Output 3: Lessons and experiences learnt are disseminated in Solomon Islands | 3-1 Good practices on 3R and landfill management identified thru the project activities are applied in other municipalities | 3-1 Workshop presentation
5 | Capacity Building
6 | Environmental Monitoring
7 | Policy,Planning, Performance
8 | Solid Waste Industry
* | Monitoring system of RS2010
Activities |  |  | Inputs
|  | Please see PO for details. | Japanese Side | Solomon Islands side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated from the government.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  |  | Loca cost support |  | Pre-condition
Cooperation of community people of the target area is obtained.

## Vol.1
Project Design Matrix (PDM) - Solomon Islands |  |  |  |  | PDM: Version 1
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of MECM, HCC and Gizo Town |  |  | Final Beneficiaries: Citizens of Solomon Islands |  | Project period: Feb, 2011 - Feb, 2016 (5 years)
Implementing Agency: MECM, HCC and Gizo Town |  |  | Target Area: Solomon Islands |  | Date issued: Feb 2013
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced. |  |  | 1.To be discussed | To be advised
1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Project Purpose |  |  | 1. # of experts (Trainers) in the field of ●● listed in the SPREP inventory | SPREP (Regional inventory of skilled people)
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 2-1 #of initiatives on waste minimization introduced 2-2 Proportion of recyclables and green waste disposed of at the landfill is decreased by XX % | 2-1 Workshop presentation 2-2 Waste characterization reports
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing
2-1 | 3Rs/4Rs | Output 1: 3R activities are practiced in Honiara and Gizo | 1-1 National Policy/Strategy for 3R is developed 1-2-1 Recycle rate increases 1-2-2 Proportion of incoming wastes at the dumpsite decreases 1-3 Level of recognition on 3Rs in Honiara and Gizo increase after implementation of activities 1-4 Draft legislation for 3Rs is developed: Deposit program, waste disposal fees, etc. 1-5-1 10 schools in Honiara develop 3R action plan 1-5-2 5 schools in Gizo develop 3R action plan 1-6-1 Three 3R pilot projects are implemented in Honiara 1-6-2 Two 3R pilot projects are implemented in Gizo | 1-1 Strategy paper for 3R
2-2 | Waste Disposal | Output 2: Waste disposal system is improved in Honiara and Gizo. | 2-1 Different types of waste materials are disposed at appropriate cells 2-2 Annual operation plan is developed 2-3-1 10 officers and operators are trained for landfill operation in Honiara 2-3-2 5 officers and operators are trained for landfill operation in Gizo 2-4 Management of Leachate is established 2-5 Waste pickers are registered and managed properly | 2-1 Operation manuals 2-2 Operation reports
2-3 | Waste Collection
3 | Legislation
4 | Awareness/Communication/Education | Output 3: Lessons and experiences learnt are disseminated in Solomon Islands | 3-1 Good practices on 3R and landfill management identified through the project activities are available in all provincial centers 3-2 Officers from each provincial government learn good practices on 3R and landfill management | 3-1 Workshop presentation
5 | Capacity Building
6 | Environmental Monitoring
7 | Policy,Planning, Performance
8 | Solid Waste Industry
* | Monitoring system of RS2010
Activities |  |  | Inputs
|  | Please see PO for details. | Japanese Side | Solomon Islands side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated from the government.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  |  | Loca cost support |  | Pre-condition
Cooperation of community people of the target area is obtained.

## Vol.2
Project Design Matrix (PDM) - Solomon Islands |  |  |  |  | PDM: Version 2
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of MECDM, HCC and Gizo Town |  |  | Final Beneficiaries: Citizens of Solomon Islands |  | Project period: Feb, 2011 - Feb, 2016 (5 years)
Implementing Agency: MECDM, HCC and Gizo Town |  |  | Target Area: Solomon Islands |  | Date issued: June 12, 2014
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced. |  |  | 1.Proportion of recyclables and green waste disposed of at the landfill is decreased by XX %. | Incoming survey
1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Project Purpose |  |  | 1. 5 experts (Trainers) listed in the SPREP inventory | SPREP (Regional inventory of skilled people)
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 2-1. 5 initiatives on waste minimization introduced 2-2. Ranadi and Gizo landfill are managed as planned in the Annual Operation Plans. 2-3. Provincial officers recognize the importance of 3R and SWM and are willing to promote 3R and SWM in their respective provinces. | 2-1 Workshop presentation 2-2 Waste characterization reports 2-1. Activities reports 2-2. Annual Operation Plan 2-3. Draft 3R activities/plan in Province
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing |  |  |  | 1. Heavy machinery necessary for landfill management is available.
2-1 | 3Rs/4Rs | Output 1: 3R activities are practiced in Honiara and Gizo | 1-1. National Solid Waste Management Strategy and Action Plan (NSWMS 2009-2014) is reviewed and NSWMS (2015-2019) is developed. 1-2. A national waste management communication strategy for 3R is developed. 1-3. More than 50% of general public in Honiara and Gizo, who are interviewed randomly, can answer what 3Rs mean. 1-4. One draft legislation for 3Rs is drafted. 1-5-1 10 schools in Honiara develop 3R action plan 1-5-2 3 schools in Gizo develop 3R action plan 1-6-1 Three 3R pilot projects are implemented in Honiara 1-6-2 Two 3R pilot projects are implemented in Gizo | 1-1 Strategy paper for National Solid Waste Management Strategy and Action Plan (NSWMS 2015-19) 1-2. Report of 3R communication Strategy 1-3. Survey Reports 1-4. Draft paper for 3Rs related legisration 1-5. Action Plan Reports 1-6. Reports for Pilot Projects
2-2 | Waste Disposal | Output 2: Waste disposal system is improved in Honiara and Gizo. | 2-1 Different types of waste materials are disposed at appropriate cells 2-2 Annual operation plan is developed 2-3-1 10 officers and operators are trained for landfill operation in Honiara 2-3-2 5 officers and operators are trained for landfill operation in Gizo 2-4 Management of Leachate is established 2-5 Waste pickers are registered and managed properly | 2-1 Operational manuals 2-2 Operational Reports 2-3. Capacity Assessment Sheet 2-4. Operational manuals 2-5. Monitoring Sheet
2-3 | Waste Collection
3 | Legislation
4 | Awareness/Communication/Education | Output 3: Lessons and experiences learnt are disseminated in Solomon Islands | 3-1 Good practices on 3R and landfill management identified through the project activities are available in all provincial centers 3-2 Officers from each provincial government learn good practices on 3R and landfill management | 3-1. Sharing the ICT materials, Manuals 3-2. Participation of the training/workshop
5 | Capacity Building
6 | Environmental Monitoring
7 | Policy,Planning, Performance
8 | Solid Waste Industry
* | Monitoring system of RS2010
Activities |  |  | Inputs
|  | Please see PO for details. | Japanese Side | Solomon Islands side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated from the government. 4. Input of JICA experts for Solomon Islands is provided timely and appropriately.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  |  | Local cost support |  | Pre-condition
Cooperation of community people of the target area is obtained.

## Vol.3
Project Design Matrix (PDM) - Solomon Islands |  |  |  |  | PDM: Version 3
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of MECDM, HCC and Gizo Town |  |  | Final Beneficiaries: Citizens of Solomon Islands |  | Project period: Feb, 2011 - Feb, 2016 (5 years)
Implementing Agency: MECDM, HCC and Gizo Town |  |  | Target Area: Solomon Islands |  | Date issued: February 3, 2015
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced. |  |  | 1.Proportion of recyclables and green waste disposed of at the landfill is decreased. | Incoming survey
1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Project Purpose |  |  | 1. 5 experts (Trainers) listed in the SPREP inventory | SPREP (Regional inventory of skilled people)
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 2-1. 5 initiatives on waste minimization introduced 2-2. Ranadi and Gizo landfill are managed as planned in the Annual Operation Plans. 2-3. Provincial officers recognize the importance of 3R and SWM and are willing to promote 3R and SWM in their respective provinces. | 2-1 Workshop presentation 2-2 Waste characterization reports 2-1. Activities reports 2-2. Annual Operation Plan 2-3. Draft 3R activities/plan in Province
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing |  |  |  | 1. Heavy machinery necessary for landfill management is available.
2-1 | 3Rs/4Rs | Output 1: 3R activities are practiced in Honiara and Gizo | 1-1. National Solid Waste Management Strategy and Action Plan (NSWMS 2009-2014) is reviewed and NSWMS (2015-2019) is developed. 1-2. A national waste management communication strategy for 3R is developed. 1-3. More than 50% of general public in Honiara and Gizo, who are interviewed randomly, can answer what 3Rs mean. 1-4. One draft legislation for 3Rs is drafted. 1-5-1 10 schools in Honiara develop 3R action plan 1-5-2 3 schools in Gizo develop 3R action plan 1-6-1 Three 3R pilot projects are implemented in Honiara 1-6-2 Two 3R pilot projects are implemented in Gizo | 1-1 Strategy paper for National Solid Waste Management Strategy and Action Plan (NSWMS 2015-19) 1-2. Report of 3R communication Strategy 1-3. Survey Reports 1-4. Draft paper for 3Rs related legisration 1-5. Action Plan Reports 1-6. Reports for Pilot Projects
2-2 | Waste Disposal | Output 2: Waste disposal system is improved in Honiara and Gizo. | 2-1 Different types of waste materials are disposed at appropriate cells 2-2 Annual operation plan is developed 2-3-1 10 officers and operators are trained for landfill operation in Honiara 2-3-2 5 officers and operators are trained for landfill operation in Gizo 2-4 Management of Leachate is established 2-5 Waste pickers are registered and managed properly | 2-1 Operational manuals 2-2 Operational Reports 2-3. Capacity Assessment Sheet 2-4. Operational manuals 2-5. Monitoring Sheet
2-3 | Waste Collection
3 | Legislation
4 | Awareness/Communication/Education | Output 3: Lessons and experiences learnt are disseminated in Solomon Islands | 3-1 Good practices on 3R and landfill management identified through the project activities are available in all provincial centers 3-2 Officers from each provincial government learn good practices on 3R and landfill management | 3-1. Sharing the ICT materials, Manuals 3-2. Participation of the training/workshop
5 | Capacity Building
6 | Environmental Monitoring
7 | Policy,Planning, Performance
8 | Solid Waste Industry
* | Monitoring system of RS2010
Activities |  |  | Inputs
|  | Please see PO for details. | Japanese Side | Solomon Islands side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated from the government. 4. Input of JICA experts for Solomon Islands is provided timely and appropriately.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  |  | Local cost support |  | Pre-condition
Cooperation of community people of the target area is obtained.