## Ver3-Mar 2015
Attachment 1: Project Design Matrix (PDM) Ver 1 - Vanuatu |  |  |  |  | PDM: Version 3
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of ●● |  |  | Final Beneficiaries: Citizens of ●● |  | Project period: Feb, 2011 - Feb, 2016 (5 years)
Implementing Agency: ●● |  |  | Target Area: ●● |  | Date issued: March 2015
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced. |  |  | 1-1. 60% of the registered experts (trainers) on the SPREP list will participate as trainers at least one workshop and/or training in region and/or in-country should there be an opportunity for them to do so. 1-2. Amounts of waste disposal at Port Vila & Luganville landfills are decreased by at least 7% respectively. | 1-1. Submission of the workshop documents 1-2. Incoming Waste Disposal Records | Registered experts wil be provided with the oppornities to participate in workshops.
Project Purpose |  |  |  |  | 1. Natural disaster would not drastically affect the collaboration mechanism of SPREP. 2. Political changes of PIC countries would not drastically affect the collaboration mechanism of SPREP.
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 1. Three experts (Trainers) are listed in the SPREP inventory. | 1. SPREP (Regional inventory of skilled people)
|  |  | 2. Bouffa and Luganville landfill are managed as planned in the Annual Operation Plans 3. One or more provinces implemented their respective action plan to promote minimizations and composting in respective provinces. | 2. Annual Operational Plans 3. Reports from the province
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing
2-1 | 3Rs/4Rs | Output 1: Waste minimization mechanisms are developed. | 1.1 Amount of organic waste generated from market is reduced by 20% (Port Vila) 1.2 NWMS is established 1.3 Collection system for cans is established | 1.1 Incoming Waste Disposal Records 1.2 Endorsement of NWMS document 1.3 Interview survey of recycling companies
2-2 | Waste Disposal | Output 2: Existing waste disposal sites (Bouffa and Lugaville) are improved. | 2.1 Manual Data management system is established in Bouffa landfill 2.2 Operation and management master plan for Bouffa landfill is utilized 2.3 Closure plan for Luganville disposal site is established | 2.1 Establishment of incoming vehicle records in Bouffa 2.2 Periodical data analysis and reporting 2.3 Annual Operational Plans 2.4 Closure Plan document is preparaed
2-3 | Waste Collection
3 | Legislation
4 | Awareness/Communication/Education
5 | Capacity Building | Output 3: Capacities for waste management at the national and local government level are enhanced. | 3.1 More than one provincial officer recognizes the importance of waste minimization and SWM. 3.2 Manual for developing Solid Waste Management master plans at province level is prepared. | 3.1 Waste Characterization Reports 3.2 Manual documetns
6 | Environmental Monitoring
7 | Policy,Planning, Performance
8 | Solid Waste Industry
* | Monitoring system of RS2010
Activities |  |  | Inputs
|  | Please see PO for details. | Japanese Side | Vanuatu side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated from the government. 4. Input of JICA experts for Vanuatu is provided timely and appropriately. 5. Power supply is available at Bouffa Landfill.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  |  | Local cost support |  | Pre-condition
Cooperation of community people of the target area is obtained.